## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP3: Establishment and equipment of the CTIs |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | An Equipped centers of innovation in all HEIs participating in the project |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Establishment of center offices and department | 1.3. 2016 | 20.4.2016 | Jordan | Each JO university has established a center of innovation and/or a unit for the collaboration with the industry. | - Number of centers - Number of units for collaboration with the industry |
| 1.2 | Hardware equipment at the Centers | 17.3.2016 | 1.12.2016 | Jordan | The list of equipment needed was finalized by the WP members. A render was submitted by JUST on March 17, 2016 to purchase the first batch of equipment needed by all JO CTIs. The Central Tenders Unit at JUST has qualified a local supplier to provide the needed equipment. It is expected that the equipment to be delivered by the first week of Dec. 2016. | 1. Number of hardware units in each CTI |
| 1.3 | Installation and adjustment of software | 1.12.2016 | 7.12.2016 | Jordan | In order to minimize the cost of equipment and software, the WP committee decided to install the software needed at each university computer center. This will save the cost of software; which will enable the partners purchase more hardware equipment. | - Number of software installed in each CTIs |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |

Changes that have occurred in this result since the original proposal:

Since non-academic JO partners are not allowed to have a budget for equipment, the units for innovation at these partner institutions are no longer needed. However, some of the partners; HCST, and ASRF, have established centers/units for innovation.