## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP5: QUALITY PLAN |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal |  |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1. | Quality Committee | 21.02.2016 | 23.02.2016 | Jordan | The Quality Committee was established during the kick-off meeting of the project that has taken place in Jordan between 21 & 23 of February 2016. It is composed of representatives from CRE.THI.DEV (Quality manager), JUST, ARCA, University of Cyprus, P&B, MU and AULE. | Minutes of kick-off meeting |
| 5.2. | Monitoring, Evaluation and Quality Plan | 08.03.2016 | 11.10.2016 | Greece | The following documents were drafted and circulated to the members of the Quality Committee for comments: Quality plan Quality plan manual Consultation Evaluation Sheet Deliverable Evaluation Sheet Document template Database and website questionnaire Evaluation Sheet for the Establishment of CTIs Event Evaluation Sheet Project Quality Assessment Quality Form Template Staff evaluation of host organisations Training-Consultation Session Evaluation Sheet Work Packages Monitoring | Quality plan manual and annexes |
| 5.3. | Reporting | 11.11.2016 | 15.11.2016 | Jordan | Six months progress reports were sent to JUST by the leaders of the WPs in order to prepare the six months progress report of the whole project. |  |
| 5.4. | External Monitor |  |  | Jordan | An external evaluator with scientific expertise on the fields of the project as well as on European projects was selected by the QC in order to verify the quality and progress of the project and the achievement of milestones and objectives and to evaluate the results of each WP. | Contract |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |

Changes that have occurred in this result since the original proposal: