## Table of achieved / planned results

| Title and reference number of the work package (WP) | WP6: Dissemination, Exploitation of results, and sustainability |
| --- | --- |
| Indicators of achievement and or/performance as indicated in the project proposal | Conducted events, produced reports and dissemination material |

Activities carried out to date to achieve this result:

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity carried out | Specific and measurable indicators of achievement |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Developing a dissemination and exploitation plan | 15-06-2016 | 30-08-2016 | Italy | Dissemination plan has been produced. Dissemination will focus on three main threads: - promoting innovation culture in the Jordan universities (through workshops and informative material dissemination), - linking universities with the business sector (through e-participation events as ETM), - fostering the entrepreneurial attitude of young people (through the website hosting a repository of information on innovation models and toolkits for developing business ideas). | Dissemination plan produced |
| 6.2 | Elaboration of project image and dissemination materials | 01-09-2016 | 15-10-2016 | Italy | The project image has been elaborated. Main tools designed were: The project logo to track documents, deliverables, etc. The coordinated layout for the information campaign to increase visibility for the project and the partnership. The leaflet to inform stakeholders on events and contribute to awareness-raising on innovation and entrepreneurship. Other tools designed: headed paper, folder, poster, rollup, power point template. Two edition of the newsletter have been produced. | Leaflets and promotional materials disseminated. Publication of information about activities of CTIs. |
| 6.3 | Organizing workshops and info-days | 15-10-2016 | 30-04-2017 | Jordan | An info day was conducted on 4th October to disseminate the project for students and academic staff at the University of Jordan. | Number of participants |
| 6.4 | Organizing an Electronic Town Meeting | 01-09-2016 | 30-10-2016 | Jordan | ETM took place in Amman on 17th October 2016. A training session was conducted for JO partners staff (moderators and rapporteurs) on 16th October 2016, to train on the ETM meeting methodology. The 56 invited participants represented most of the stakeholders of the project. The INVENT ETM event was divided into 5 discussion sessions and the participants were allocated to 10 Separate discussion tables, participants on each table should be from different background to heat the debate. Each session had different debate title but in the same time related to general theme. During each session the participants were asked to express their opinion in electronic polls related to the session. After the last session the Event Manger summarised the Instant Report to the participants together with the polls results and the main conclusions and outcomes of all debates and discussions. | ETM organized. Number of participants to the ETM. |

Activities to be carried out to achieve this outcome (before the end of the project)

| Activity N° | Activity Title | Start date | End date | Place | Description of the activity to be carried out | Specific and measurable indicators of progress |
| --- | --- | --- | --- | --- | --- | --- |
| 6.2 | Elaboration of project image and dissemination materials | - | 15-10-2016 | - | New editions of the newsletter to be produced and disseminated each six months. | Number of material produced |
| 6.3 | Organizing workshops and info-days | 15-11-2016 | 30-04-2017 | Jordan | Informative workshops will be held at University departments and informative materials will be distributed using an interactive approach to elicit ideas during the info sessions and encouraging an ice-breaking climate among participants to share knowledge. Students and researchers will be involved for an active role during the events and also for the choice of most appropriate channels and tools for communication. | Number of organized workshops |
| 6.5 | Organizing Local Final Conference | 01-09-2018 | 30-09-2018 | Jordan | A Final conference will be organized at JUST at the end of project. It will allow the exchange between project members and stakeholders to promote the next edition of the INVENT project. The final dissemination event will present to the general audience the project outcomes. |  |
| 6.6 | Developing a sustainability plan | 01-02-2018 | 31-08-2018 | Italy, Jordan | Key stakeholder groups will include future programme funders, policy makers, enterprise networks, business districts. The partnership will raise awareness among territorial stakeholders about the opportunity offered by the deployment of innovation networks between R&D performers and private players to generate technology transfer flows, knowledge-based companies and more qualified jobs for young people. Mapping in a data base the stakeholders interested in the project results will customize the approach, get them actively involved through ongoing consultation and prepare follow-up actions under the end of EU funding. Thematic meetings with policy makers will be used to show the lessons learnt, the benefits gained and the return on investments of innovation in the academic system and joint actions gathering public and private actors. Memoranda of Understanding will be drawn up and signed by local authorities, higher education institutes, business communities and research/innovation centres to foster technology transfer and innovative entrepreneurship. |  |

Changes that have occurred in this result since the original proposal:

No changes have occurred.